## Purpose
1 | Project Summary
2 | Project Completed Work
3 | Project Work In Progress
4 | Project Pendings
5 | Invoice Duration
6 | Invoice Completed
7 | CWR Monitoring
8 | RO Monitoring
9 | Completed Dates
10 | Monthly Progress
11 | Monthly Issued & Completed Quantity

## BOQ MASTER
CONTRACT # GTC=1236/2024-11KV Reinforcement works -BOQ-MASTER STATUS
SL | CWR | CWR No. | Work Order | Scheme Number | Received Date | CWR Start Date | RO Number | RO STATUS | RO approved Date | RO End Date | CWR Completion Date | Backfilled Date/Reisntatement Date/Shut Down/Return Date/ | Date Type | KPI | Type of job | Total Days | Priority | SITE STATUS | Baladiya Permit | SS no | Location | Zone | 1.1 - Excavation HV/PILOT |  | 1.2 Road crossing duct Exisiting |  | 1.3 Roadcrossing duct future |  | 1.4 Reinstatement |  | 1.5 Green special tiles |  | 1.6 Phase-2 |  | 1.7 Supply and install HDPE Pipe(2x150mm) |  | 2.1 Termination HV |  | 2.2 Termination Pilot &Marshelling box |  | 2.3 Supply 11 kV ST Joint |  | 2.4 Supply Pilot ST Joint |  | 3.1 Commisioning Test |  | 4.1 Supply and install 40 mm HDPE Pipe |  | 4.2 FO CABLE BLOWN |  | 4.3 Fiber Joint |  | 4.4 fo termination 24c |  | 4.5 OTB SS |  | 4.6 OTB PRY |  | 4.7 JRC-4 Manhole |  | 4.8 Patch Chord |  | 4.9 Testing of 24c fo |  | Value |  | Final Status | Scheme Closure Form | Invoice Status | WCC Status | Invoice No. # | KM-CWR | Billing Certificate No | KM-Invoiced AMT | Trench Inspection Date | Final Inspection Status | Final Site Status
[23 empty] | EEC 61526 |  | EEC 61541 |  | EEC 61542 |  | EEC 61543 |  | EEC 154309 |  | EEC 158944 |  | EEC 75159 |  | EEC 61528 |  | EEC 61531 |  | EEC 61527 |  | EEC 61532 |  | EEM 61616 |  | E98116124 |  | EES 141860 |  | E67141444 |  | Eec 158945 |  | EES 141863 |  | EEC 158946 |  | ESs 141864 |  | EEC 158947 |  | EES 141865 |  | Issued | Completed
[23 empty] | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. |  |  | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp. | Issued | Comp.
1 | 1 | 241764 | 1166928 | 1A-624-2024 | 2025-11-16 | 2025-11-15 | NA | Not Applied | NA | NA | 2026-05-15 | 2026-09-12 | Returned | 0 | Reinforcement Normal | 301 | Low | Cancelled | Cancelled | 13815 | Umm Slal | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | Cancelled | Cancelled | Not Required | Cancelled | 1 |  | N/A | N/A | Not Required | Cancelled
2 | 2 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-09-12 | Work In Progress |  | Reinforcement Normal | 301 | High | Work In Progress | Pending | 24031 | AL Khulaifat | 56 | 300 |  |  |  | 0 | 0 | 100 |  | 50 |  |  |  | 0 |  | 5 |  | 0 | 0 | 11 |  | 10 |  | 35 |  |  |  | 6000 |  | 1 |  | 5 |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5 |  | 81055 | 0 | Work In Progress | Work In Progress | Pending | Pending | Pending | 2 |  | 0 | PENDING | Pending | Hold By KM
3 | 2-P1 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-01-06 | Backfilling | 30 | RI-Primary SS | 46058 | High | Invoiced | Not Required | 24031 | AL Khulaifat | 56 | 871.72 | 871.72 | 68.08 | 68.08 | 0 | 0 | 2 | 2 | 0 | 0 | 78 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64803.32 | 64803.32 | Invoiced | Not Required | Invoiced | Received | INV-03 | 2-P1 | 003 | 64803.32 | 2025-12-14 | Received | Invoiced
4 | 2-P2 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-01-12 | Backfilling | 30 | RI-Primary SS | 58 | High | Invoiced | Not Required | 24031 | AL Khulaifat | 56 | 649.41 | 649.41 | 136.06 | 136.06 |  |  | 186 | 186 |  |  | 123.5 | 123.5 | [6 empty] | 4 | 4 | 1 | 1 | [20 empty] | 72430.35 | 72430.35 | Invoiced | Not Required | Invoiced | Received | INV-04 | 2-P2 | 008 | 72430.35 | 2025-12-17 | Received | Invoiced
5 | 2-P3 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-07-16 | Reinstatement | 20 | RI-Primary SS | 243 | High | Completed | Not Required | 24031 | AL Khulaifat | 56 | 2345 | 2345 | 334.5 | 334.5 |  |  | 616 | 616 |  |  | 280 | 280 | [6 empty] | 8 | 8 | 1 | 1 |  |  | 1284 | 1284 | [16 empty] | 221974.5 | 221974.5 | Invoiced | Not Required | Invoiced | Received | INV-08 | 2-P3 |  | 221974.5 | 2026-02-25 | Pending | Invoiced
6 | 2-P4 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-04-15 | Reinstatement | 20 | RI-Primary SS | 151 | High | Invoiced | Not Required | 24031 | AL Khulaifat | 56 | 241.66 | 241.66 | 33.36 | 33.36 | 0 | 0 | 184 | 184 | 0 | 0 | 41.7 | 41.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | [16 empty] | 28574.7 | 28574.7 | Invoiced | Not Required | Invoiced | Received | INV-04 | 2-P4 |  | 28574.7 | 2026-03-26 | Received | Invoiced
7 | 2-P5 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-04-27 | Backfilling | 30 | RI-Primary SS | 163 | High | Invoiced | Pending | 24031 | AL Khulaifat | 56 | 1421 | 1421 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 354 | 354 | 0 | 0 | 0 | 0 | 2 | 2 |  | 0 | 0 |  | 1000 | 1000 | [16 empty] | 305233 | 305233 | Invoiced | Not Required | Invoiced | Received | INV-06 | 2-P5 |  | 305233 | 2026-03-26 | Received | Invoiced
8 | 2-P6 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-07-29 | Reinstatement | 20 | RI-Primary SS | 256 | High | Invoiced | Pending | 24031 | AL Khulaifat | 56 | 1351.24 | 1351.24 | 0 | 0 | 0 | 0 | 986 | 986 | 20 | 20 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 1 | 1 | 0 |  | 411 | 411 | [16 empty] | 125242.72 | 125242.72 | Invoiced | Not Required | Invoiced | Received | INV-09 | 2-P6 |  | 125242.72 | 2026-03-29 | Received | Invoiced
9 | 2-P7 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-04-23 | Backfilling | 30 | RI-Primary SS | 159 | High | Invoiced | Pending | 24031 | AL Khulaifat | 56 | 202.3 | 202.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 1 | 0 |  | 175 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13196.9 | 13196.9 | Invoiced | Not Required | Invoiced | Received | INV-06 | 2-P7 |  | 13196.9 | 2026-04-09 | Received | Invoiced
10 | 2-P8 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-04-26 | Backfilling | 30 | RI-Primary SS | 162 | High | Invoiced | Pending | 24031 | AL Khulaifat | 56 | 242.08 | 242.08 | 33.08 | 33.08 | 0 | 0 | 132 | 132 | 0 | 0 | 41.35 | 41.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26446.4 | 26446.4 | Invoiced | Not Required | Invoiced | Received | INV-09 | 2-P8 |  | 26446.4 | 2026-04-12 | Received | Invoiced
11 | 2-P9 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-05-03 | Backfilling | 30 | RI-Primary SS | 169 | High | Invoiced | Pending | 24031 | AL Khulaifat | 56 | 480.08 | 480.08 | 39.84 | 39.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28511.92 | 28511.92 | Invoiced | Not Required | Invoiced | Received | INV-09 | 2-P9 |  | 28511.92 | 2026-04-21 | Received | Invoiced
12 | 2-P10 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-04-28 | Backfilling | 30 | RI-Primary SS | 164 | High | Invoiced | Pending | 24031 | AL Khulaifat | 56 | 455.29 | 455.29 | 130.08 | 130.08 | 0 | 0 | 438 | 438 | 0 | 0 | 140 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72796.53 | 72796.53 | Invoiced | Not Required | Invoiced | Received | INV-09 | 2-P10 |  | 72796.53 | 2026-04-27 | Received | Invoiced
13 | 2-P11 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-07-25 | Backfilling | 30 | RI-Primary SS | 252 | High | Completed | Pending | 24031 | AL Khulaifat | 56 | 370 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 288 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205290 | 205290 | Completed | Pending | Pending | Pending | Pending | 2-P11 |  | 0 | 2026-07-23 | Pending | Completed
14 | 2-P12 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/ 821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-07-25 | Backfilling | 30 | RI-Primary SS | 252 | High | Completed | Pending | 24031 | AL Khulaifat | 56 | 291 | 291 | 0 | 0 | 0 | 0 | 113 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570 | 570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21083 | 21083 | Completed | Pending | Pending | Pending | Pending | 2-P12 |  | 0 | 2026-07-20 | Pending | Completed
15 | 2-P13 | 241765 | 1166932 | 1A-129-2025 | 2025-11-16 | 2025-11-15 | 821319/821401 | Approved/ Printed | 2026-04-17 | 2026-10-14 | 2026-12-15 | 2026-09-12 | Work In Progress | 30 | RI-Primary SS | 301 | High | Work In Progress | Required | 24031 | AL Khulaifat | 56 | 343 | 343 | 108 | 108 | 0 | 0 | 151 | 151 | 0 | 0 | 45 | 45 | 408 | 408 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302360 | 302360 | Completed | Pending | Pending | Pending | Pending | 2-P13 |  | 0 | 2026-08-26 | Pending | Cable Laying Pending
16 | 3 | 241767 | 116691 | 1A-696-2025 | 2025-11-16 | 2025-11-15 | Pending | Pending | Pending | Pending | 2026-05-15 | 2026-05-02 | Backfilling | 30 | RI-Load Flow | 168 | High | Completed | Pending | 23510 | Umm Slal | 71 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | 80 | 0 |  |  |  | 2 | 2 | 0 |  | 0 |  | 2 | 2 | 2 | 2 | 5820 | 5820 | Completed | Pending | Pending | Not Required | Pending | 3 | 012 | 0 | 2026-02-26 | Pending | Completed
17 | 4 Phase-2 | 241768 | 1166997 | 1A-14-2025 | 2025-11-16 | 2025-11-15 | 828238 | Approved/ Printed | 2026-06-06 | 2026-12-03 | 2026-05-15 | 2026-01-10 | Backfilling | 30 | Reinforcement Normal | 56 | High | Invoiced | Not Required | P576 | Umm Slal | 71 | 0 | 0 | 295.4 | 295.4 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45845.8 | 45845.8 | Invoiced | Not Required | Invoiced | Received | INV-07 | 4-PHASE-2 | 011 | 45845.8 | 2025-12-15 | Received | Invoiced
18 | 4 P1 | 241768 | 1166997 | 1A-14-2025 | 2025-11-16 | 2025-11-15 | 828238 | Approved/ Printed | 2026-06-06 | 2026-12-03 | 2026-05-15 | 2026-07-01 | Backfilling | 30 | Reinforcement Normal | 228 | High | Completed | Not Required | P576 | Umm Slal | 71 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 2800 | Completed | Pending | Pending | Pending | Pending | 4-P2 |  | 0 | 2026-06-28 | Pending | Completed
19 | 4 P2 | 241768 | 1166997 | 1A-14-2025 | 2025-11-16 | 2025-11-15 | 828238 | Approved/ Printed | 2026-06-06 | 2026-12-03 | 2026-05-15 | 2026-07-01 | Backfilling | 30 | Reinforcement Normal | 228 | High | Completed | Not Required | P576 | Umm Slal | 71 | 171 | 171 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10463 | 10463 | Completed | Pending | Pending | Work In Progress | Pending | 4-P2 |  | 0 | 2026-07-07 | Pending | Completed
20 | 4 P3 | 241768 | 1166997 | 1A-14-2025 | 2025-11-16 | 2025-11-15 | 828238 | Approved/ Printed | 2026-06-06 | 2026-12-03 | 2026-05-15 | 2026-07-01 | Backfilling | 30 | Reinforcement Normal | 228 | High | Completed | Not Required | P576 | Umm Slal | 71 | 510 | 510 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 14 | 14 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44600 | 44600 | Completed | Pending | Pending | Work In Progress | Pending | 4-P3 |  | 0 | 2026-07-12 | Pending | Completed
21 | 4-P4 | 241768 | 1166997 | 1A-14-2025 | 2025-11-16 | 2025-11-15 | 828238 | Approved/ Printed | 2026-06-06 | 2026-12-03 | 2026-05-15 | 2026-07-01 | Backfilling | 30 | Reinforcement Normal | 228 | High | Completed | Not Required | P576 | Umm Slal | 71 | 158 | 158 |  |  |  |  | 25 | 25 | [10 empty] | 13 | 13 | 12 | 12 | 5 | 5 | [18 empty] | 22109 | 22109 | Completed | Pending | Pending | Work In Progress | Pending | 4-P4 |  |  | 2026-08-16 | Pending | Completed
22 | 5 | 241785 | 1167084 | 1A-749-2025 | 2025-11-16 | 2025-11-15 | RO NA | Not Applied | N/A | N/A | 2026-05-15 | 2026-09-12 | Shut Down | 30 | Scheme Normal | 301 | High | Invoiced | Not Required | N/A | Umm Slal | 71 | [16 empty] | 7 | 7 | [24 empty] | 3150 | 3150 | Invoiced | Closed | Invoiced | Not Required | INV-01 | 5 | 001 | 3150 | 2025-11-25 | Received | Invoiced
23 | 6 | 241930 | 1169223 | 1A-26-2014 | 2025-11-19 | 2025-11-18 | RO NA | RO Not Required | N/A | N/A | 2026-05-18 | 2026-09-12 | Work In Progress |  | Scheme Normal | 298 | High | Work In Progress | Pending | 10026 | Mesaieed-Town | 92 | 50 |  | 0 | 0 | 0 | 0 | 100 |  | 0 | 0 | 0 | 0 |  |  | 1 |  | 1 |  | 0 |  | 0 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8155 | 0 | Work In Progress | Pending | Pending | Pending | Pending | 6 |  | 0 | PENDING | Pending | Work In Progress
24 | 6-P1 | 241930 | 1169223 | 1A-26-2014 | 2025-11-19 | 2025-11-18 | RO NA | RO Not Required | N/A | N/A | 2026-05-18 | 2026-09-12 | Work In Progress |  | Scheme Normal | 298 | High | Work In Progress | Pending | 10026 | Mesaieed-Town | 92 | 150 | 150 |  |  |  |  | 150 | 150 | [10 empty] | 1 | 0 | 1 | 0 | [20 empty] | 14715 | 13950 | Work In Progress | Pending | Pending | Pending | Pending | 6-P1 |  |  | 2026-08-31 | Pending | Work In Progress
25 | 7 | 241931 | 1169224 | 1A-339-2023 | 2025-11-19 | 2025-11-18 | RO NA | RO Not Required | N/A | N/A | 2026-05-18 | 2026-09-12 | Work Not Started |  | Scheme Normal | 298 | High | Pending | Pending | 21576 | Mesaieed-Industrial Area | 93 | 120 |  | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 62 |  | 2 |  | 2 |  | 6 |  | 6 |  | 4 | [19 empty] | 54790 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 7 |  | 0 | PENDING | Pending | Hold By KM
26 | 8 | 241932 | 1169225 | 1A-183-2025 | 2025-11-19 | 2025-11-18 | RO NA | RO Not Required | N/A | N/A | 2026-11-18 | 2026-09-12 | Work Not Started |  | Scheme Normal | 298 | High | Pending | Pending | 17091 | New District of Doha | 66 | 4150 |  | 880 |  | 0 | 0 | 2000 |  | 1500 |  | 250 |  | 0 | 0 | 0 | 0 | 0 | 0 | 25 |  | 25 |  | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 545835 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 8 |  | 0 | PENDING | Pending | Hold By KM
27 | 9 | 241933 | 1169226 | 1A-225-2023 | 2025-11-19 | 2025-11-18 | 814967 | Approved/ Printed | 2026-01-28 | 2026-07-23 | 2027-12-02 | 2026-09-12 | Work In Progress |  | Scheme Normal | 298 | High | Pending | Pending | 18307 | Raudat Rashid | 82 | 1257 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 6 |  | 6 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72716 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 9 |  | 0 | PENDING | Pending | Hold By KM
28 | 10-P1 | 241934 | 1169228 | 1A-172-2024 | 2025-11-19 | 2025-11-18 | Pending | Pending | Pending | Pending | 2026-05-18 | 2026-02-15 | Backfilling | 30 | Scheme Normal | 89 | High | Invoiced | Not Required | 17721 | Al Shahhniya | 80 | 513.55 | 513.55 | 64.14 | 64.14 | 0 | 0 | 0 | 0 | 0 | 0 | 53.45 | 53.45 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 23 | 23 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63769.93 | 63769.93 | Invoiced | Closed | Invoiced | Received | INV-05 | 10-P1 | 006 | 63769.93 | 2025-12-10 | Received | Invoiced
29 | 10-P2 | 241934 | 1169228 | 1A-172-2024 | 2025-11-19 | 2025-11-18 | Pending | Approved/ Printed | Pending | Pending | 2026-05-18 | 2026-03-15 | Backfilling | 30 | Scheme Normal | 117 | High | Invoiced | Not Required | 17721 | Al Shahhniya | 80 | 58 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3839 | 3839 | Invoiced | Closed | Invoiced | Received | INV-02 | 10-P2 | 007 | 3839 | 2025-12-29 | Received | Invoiced
30 | 10-P3 | 241934 | 1169228 | 1A-172-2024 | 2025-11-19 | 2025-11-18 | Pending | Pending | Pending | Pending | 2026-05-18 | 2026-01-13 | Backfilling | 30 | Scheme Normal | 56 | High | Invoiced | Not Required | 17721 | Al Shahhniya | 80 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 1113 | Invoiced | Closed | Invoiced | Received | INV-05 | 10-P3 | 006 | 1113 | 2025-12-29 | Received | Invoiced
31 | 10-P4 | 241934 | 1169228 | 1A-172-2024 | 2025-11-19 | 2025-11-18 | Pending | Pending | Pending | Pending | 2026-05-18 | 2026-02-22 | Backfilling | 30 | Scheme Normal | 96 | High | Invoiced | Not Required | 17721 | Al Shahhniya | 80 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 3 | 3 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9630 | 9630 | Invoiced | Closed | Invoiced | Received | INV-05 | 10-P4 | 006 | 9630 | 2026-01-13 | Received | Invoiced
32 | 11 | 241935 | 1169231 | 1A-3597-2020 | 2025-11-19 | 2025-11-18 | RO NA | RO Not Required | N/A | N/A | 2027-12-02 | 2026-09-12 | Work Not Started |  | Scheme Normal | 298 | High | Pending | Pending | P086 | UMM BAB | 84 | 1690 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  | 2 |  | 8 |  | 8 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98700 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 11 |  | 0 | PENDING | Pending | Hold By KM
33 | 11-SD | 241935 | 1169231 | 1A-3597-2020 | 2025-11-19 | 2025-11-18 | RO NA | RO Not Required | N/A | N/A | 2026-05-18 | 2026-07-01 | Backfilling | 30 | Scheme Normal | 225 | High | Pending | Pending | P086 | UMM BAB | 84 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460 | 1460 | Completed | Not Required | Pending | Work In Progress | Pending | 11-SD |  |  | 2026-06-04 | Pending | Completed
34 | 12 | 242008 | 1170101 | 4-179-2022 | 2025-11-23 | 2025-11-22 | 823951 | Approved/ Printed | 2026-05-14 | 2026-10-15 | 2026-06-18 | 2026-09-12 | Work In Progress |  | Scheme Normal | 294 | High | Pending | Pending | 10829 | Al Kheesa | 70 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Work In Progress | Pending | Pending | Work In Progress | Pending | 12 |  | 0 | PENDING | Pending | Hold By KM
35 | 12-P1 | 242008 | 1170101 | 4-179-2022 | 2025-11-23 | 2025-11-22 | 823951 | Approved/ Printed | 2026-05-14 | 2026-10-15 | 2026-06-18 | 2026-09-12 | Backfilling | 30 | Scheme Normal | 294 | High | Work In Progress | Pending | 10829 | Al Kheesa | 70 | 238 | 238 |  |  |  |  | 236 | 236 | [6 empty] | 0 |  |  | 0 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23499 | 23499 | Completed | Pending | Pending | Work In Progress | Pending | 12-P1 |  |  | 2026-08-12 | Pending | Reinstatement Pending
36 | 13 | 242009 | 1170103 | 29-253-2022 | 2025-11-23 | 2025-11-22 | Cancelled | Not Applied | Cancelled | Cancelled | 2026-05-18 | 2026-09-12 | Returned | 0 | Scheme Normal | 294 | High | Pending | Pending | 39552 | Al Kharara | 95 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | Cancelled | Cancelled | Not Required | Cancelled | 13 |  | 0 | N/A | Not Required | Cancelled
37 | 14-P1 & P2 | 242010 | 1170107 | 1A-252-2025 | 2025-11-23 | 2025-11-22 | 809996/ 812700 | Approved/ Printed | 2025-12-13 | 2026-06-11 | 2026-05-22 | 2026-04-05 | Backfilling | 30 | Scheme Normal | 134 | High | Invoiced | Required | 1206 | Al Wukair | 91 | 416.13 | 416.13 | 0 | 0 | 0 | 0 | 293 | 293 | 95 | 95 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43934.89 | 43934.89 | Invoiced | Closed | Invoiced | Received | INV-04 | 14-P1 & P2 | 013 | 43934.89 | 2026-01-28 | Received | Invoiced
38 | 15-P1 | 242011 | 1170110 | 1A-881-2025 | 2025-11-23 | 2025-11-22 | 809997 | Approved/ Printed | 2025-12-13 | 2026-06-11 | 2026-05-22 | 2026-03-15 | Shut Down | 30 | Scheme Normal | 113 | High | Invoiced | Not Required | 9790 | Al Kheesa | 70 | 470.88 | 470.88 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30906.64 | 30906.64 | Invoiced | Closed | Invoiced | Received | INV-02 | 15-P1 | 005 | 30906.64 | 2025-12-23 | Received | Invoiced
39 | 16 | 242148 | 1171682 | 1A-910-2025 | 2025-11-25 | 2025-11-24 | NA | Not Applied | NA | NA | 2026-05-23 | 2026-09-12 | Returned | 0 | Scheme Normal | 292 | High | Cancelled | Cancelled | 37762 | Raudat Rashid | 82 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | Cancelled | Cancelled | Not Required | Cancelled | 16 |  | 0 | N/A | Not Required | Cancelled
40 | 17-P1 | 242152 | 1171691 | 1A-198-2024 | 2025-11-25 | 2025-11-24 | 812610 | Approved/ Printed | 2026-01-19 | 2026-07-02 | 2026-05-24 | 2026-04-14 | Backfilling | 30 | Scheme Normal | 141 | High | Invoiced | Not Required | 25231 | Al Wukair | 91 | 40 | 40 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 13 | 13 | 12 | 12 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15210 | 15210 | Invoiced | Not Required | Invoiced | Received | INV-05 | 17-P1 |  | 15210 | 2026-04-01 | Received | Invoiced
41 | 18 | 242155 | 1171696 | 1A-78-2024 | 2025-11-25 | 2025-11-24 | Pending | Pending | Pending | Pending | 2026-05-24 | 2026-09-12 | Work Not Started |  | Scheme Normal | 292 | High | Pending | Not Required | 2007 | Murrah / Al Aziziya | 55 |  |  | 0 | 0 | 0 | 0 | 25 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 |  | 6 |  | 8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10190 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 18 |  | 0 | PENDING | Pending | Hold By KM
42 | 18-P1 | 242155 | 1171696 | 1A-78-2024 | 2025-11-25 | 2025-11-24 | Pending | Approved/ Printed | Pending | Pending | 2026-05-24 | 2026-02-05 | Shut Down | 30 | Scheme Normal | 73 | High | Invoiced | Not Required | 2007 | Murrah / Al Aziziya | 55 | 41 | 41 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10783 | 10783 | Invoiced | Closed | Invoiced | Received | INV-02 | 18-P1 | 004 | 10783 | 2026-02-02 | Received | Invoiced
43 | 19 | 242156 | 1171700 | 1A-7-2024 | 2025-11-25 | 2025-11-24 | Pending | Pending | Pending | Pending | 2026-05-24 | 2026-09-12 | Work Not Started |  | Scheme Normal | 292 | High | Pending | Pending | 4481 | Al Aziziya | 55 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1340 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 19 |  | 0 | PENDING | Pending | Hold By KM
44 | 20 | 242195 | 1172151 | 1A-598-2025 | 2025-11-26 | 2025-11-25 | RO NA | Not Applied | N/A | N/A | 2026-05-25 | 2026-09-12 | Shut Down | 30 | Scheme Normal | 291 | High | Invoiced | Not Required | N/A | Al Khulaifat Al Jadeeda | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25200 | 25200 | Invoiced | Closed | Invoiced | Not Required | INV-01 | 5 | 002 | 25200 | 2025-11-25 | Received | Invoiced
45 | 21-P1 | 242196 | 1172157 | 1A-31-2021 | 2025-11-26 | 2025-11-25 | 809906/ 827885 | Approved/ Printed | 2026-01-07 | 2026-12-23 | 2026-05-25 | 2026-09-12 | Reinstatement | 20 | Scheme Normal | 291 | High | Completed | Pending | P086 | Bin Omran | 37 | 310 | 310 |  |  | 0 | 0 | 780 | 780 | 480 | 480 |  |  | 345 | 345 |  |  |  |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305110 | 305110 | Completed | Pending | Pending | Pending | Pending | 21-P1 |  |  | 2026-06-01 | Pending | Reinstatement Pending
46 | 21-P2 | 242196 | 1172157 | 1A-31-2021 | 2025-11-26 | 2025-11-25 | 809906/ 827885 | Approved/ Printed | 2026-01-07 | 2026-12-23 | 2026-05-25 | 2026-07-02 | Reinstatement | 20 | Scheme Normal | 219 | High | Completed | Pending | P086 | Bin Omran | 37 | 426 | 426 | 72 | 72 | 0 | 0 | 350 | 350 | 195 | 195 |  |  | 260 | 260 |  |  |  |  | 16 | 16 | 13 | 13 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238007 | 238007 | Completed | Pending | Pending | Pending | Pending | 21-P2 |  |  | 2026-06-04 | Pending | Reinstatement Pending
47 | 22 | 242733 | 1176740 | 1A-792/2025 | 2025-12-09 | 2025-12-08 | 811083 | Approved/ Printed | 2025-12-23 | 2026-06-11 | 2026-06-09 | 2026-05-24 | Backfilling | 30 | Scheme Normal | 167 | High | Invoiced | Not Required | P599 | Al Wukair | 91 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6685 | 6685 | Invoiced | Closed | Invoiced | Received | INV-06 | 22 |  | 6685 | 2026-02-02 | Received | Invoiced
48 | 23-P1 & P2 | 242995 | 1178134 | 1A-904-2025 | 2025-12-14 | 2025-12-13 | 811841 | Approved/ Printed | 2026-01-12 | 2026-06-25 | 2025-06-14 | 2026-03-08 | Backfilling | 30 | Scheme Normal | 85 | High | Invoiced | Pending | 11956 | Al Kheesa | 70 | 566.72 | 566.72 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 6 | 6 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36536.16 | 36536.16 | Invoiced | Closed | Invoiced | Received | INV-06 | 23-P2 | 009 | 36536.16 | 2026-02-25 | Received | Invoiced
49 | 24 | 244310 | 1187940 | 1A-25/2019 | 2026-01-08 | 2026-01-07 | 822694 | Approved/ Printed | 2026-05-09 | 2026-09-15 | 2026-06-07 | 2026-09-12 | Work In Progress |  | Scheme Normal | 248 | High | Work In Progress | Required | P417 | Al Doha Al Jadeeda |  | 500 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56180 | 0 | Work In Progress | Pending | Pending | Work In Progress | Pending | 24 |  | 0 | PENDING | Pending | Work In Progress
50 | 25 | 244395 | 1188979 | 1A-866/2025 | 2026-01-12 | 2026-01-11 | 815394 | Approved/ Printed | 2026-02-08 | 2026-07-30 | 2026-06-11 | 2026-03-31 | Backfilling | 30 | Scheme Normal | 79 | High | Invoiced | Not Required | 2382 | Al Madar Al Qadeem | 45 | 169.16 | 169.16 | 0 | 0 | 0 | 0 | 170 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 1 | 2 | 2 | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21080.48 | 21080.48 | Invoiced | Closed | Invoiced | Received | INV-03 | 25 | 010 | 21080.48 | 2026-02-22 | Received | Invoiced
51 | 26-P-1 | 244397 | 1188982 | 1A-869/2025 | 2026-01-12 | 2026-01-11 | 815395 | Approved/ Printed | 2026-02-08 | 2026-07-30 | 2026-06-11 | 2026-04-06 | Backfilling | 30 | Scheme Normal | 67 | High | Invoiced | Pending | 19523 | Al Madar Al Qadeem | 45 | 436.98 | 436.98 | 0 | 0 | 0 | 0 | 224 | 224 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88119.94 | 88119.94 | Invoiced | Closed | Invoiced | Received | INV-09 | 26-P1 |  | 88119.94 | 2026-03-19 | Received | Invoiced
52 | 26-P-2 | 244397 | 1188982 | 1A-869/2025 | 2026-01-12 | 2026-01-11 | 815395 | Approved/ Printed | 2026-02-08 | 2026-07-30 | 2026-06-11 | 2026-04-13 | Backfilling | 30 | Scheme Normal | 67 | High | Invoiced | Pending | 19523 | Al Madar Al Qadeem | 3 | 238 | 238 | 0 | 0 | 0 | 0 | 36 | 36 | 0 | 0 | 1432 | 1432 | 0 | 0 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221944 | 221944 | Invoiced | Closed | Invoiced | Received | INV-07 | 26-P2 |  | 221944 | 2026-04-01 | Received | Invoiced
53 | 27-P1 | 244765 | 1191065 | 1A-829/2025 | 2026-01-18 | 2026-01-17 | 815396 | Approved/ Printed | 2026-02-08 | 2026-06-30 | 2026-07-18 | 2026-04-22 | Backfilling | 30 | Scheme Normal | 95 | High | Invoiced | Not Required | 39278 | Al Mansoura/Bin Dirham | 25 | 225.05 | 225.05 |  |  | 0 | 0 | 197 | 197 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53392.65 | 53392.65 | Invoiced | Closed | Invoiced | Received | INV-05 | 27 |  | 53392.65 | 2026-03-19 | Received | Invoiced
54 | 28-P-1 | 245374 | 1194764 | 1A-917/2025 | 2026-01-26 | 2026-01-25 | 816607 | Approved/ Printed | 2026-02-19 | 2026-08-06 | 2026-07-26 | 2026-04-15 | Backfilling | 30 | Scheme Normal | 80 | High | Invoiced | Not Required | 35928 | Al Nasraniya | 85 | 241.07 | 241.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12776.71 | 12776.71 | Invoiced | Closed | Invoiced | Received | INV-03 | 28-P1 | 018 | 12776.71 | 2026-03-26 | Received | Invoiced
55 | 28-P-2 | 245374 | 1194764 | 1A-917/2025 | 2026-01-26 | 2026-01-25 | 816607 | Approved/ Printed | 2026-02-19 | 2026-08-06 | 2026-07-26 | 2026-04-15 | Backfilling | 30 | Scheme Normal | 80 | High | Invoiced | Pending | 35928 | Al Nasraniya | 70 | 243.25 | 243.25 | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 345 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68702.25 | 68702.25 | Invoiced | Closed | Invoiced | Received | INV-08 | 28-P-2 |  | 68702.25 | 2026-04-02 | Received | Invoiced
56 | 29-P1 | 245446 | 1195100 | 1A-1371/2021 | 2026-01-27 | 2026-01-26 | 816608/ 827265/ 836330 | Approved/ Printed | 2026-02-16 | 2026-11-16 | 2026-10-26 | 2026-05-17 | Backfilling | 30 | Scheme Normal | 111 | High | Invoiced | Not Required | 35268 | Al Kheesa | 70 | 224.39 | 224.39 | 0 | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13212.67 | 13212.67 | Invoiced | Not Required | Invoiced | Received | INV-07 | 29-P1 |  | 13212.67 | 2026-05-05 | Received | Invoiced
57 | 29-P2-Joints | 245446 | 1195100 | 1A-1371/2021 | 2026-01-27 | 2026-01-26 | 816608/ 827265/ 836330 | Approved/ Printed | 2026-02-16 | 2026-11-16 | 2026-10-26 | 2026-09-12 | Backfilling | 30 | Scheme Normal | 229 | High | Work In Progress | Pending | 35268 | Al Kheesa | 70 | 0 | 0 | [12 empty] | 1 | 1 | 1 | 1 | [24 empty] | 930 | 930 | Completed | Pending | Pending | Pending | Pending | 29-P2 |  |  | 2026-06-16 | Pending | Completed
58 | 29-P3 | 245446 | 1195100 | 1A-1371/2021 | 2026-01-27 | 2026-01-26 | 816608/ 827265/ 836330 | Approved/ Printed | 2026-02-16 | 2026-11-16 | 2026-10-26 | 2026-09-12 | Backfilling | 30 | Scheme Normal | 229 | High | Work In Progress | Pending | 35268 | Al Kheesa | 70 | 548 | 548 | [6 empty] | 60 | 60 | [8 empty] | 7 | 7 | 4 | 4 | [20 empty] | 38644 | 38644 | Completed | Pending | Pending | Pending | Pending | 29-P3 |  |  | 2026-07-20 | Pending | Completed
59 | 29-P4 | 245446 | 1195100 | 1A-1371/2021 | 2026-01-27 | 2026-01-26 | 816608/ 827265/ 836330 | Approved/ Printed | 2026-02-16 | 2026-11-16 | 2026-10-26 | 2026-09-12 | Backfilling | 30 | Scheme Normal | 229 | High | Work In Progress | Pending | 35268 | Al Kheesa | 70 | 176 | 176 |  |  |  |  | 176 | 176 | 0 | 0 | 0 | 0 | 28 | 28 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37348 | 37348 | Completed | Pending | Pending | Pending | Pending | 29-P4 |  |  | 2026-07-26 | Pending | Completed
60 | 29-P5 | 245446 | 1195100 | 1A-1371/2021 | 2026-01-27 | 2026-01-26 | 816608/ 827265/ 836330 | Approved/ Printed | 2026-02-16 | 2026-11-16 | 2026-10-26 | 2026-09-12 | Backfilling | 30 | Scheme Normal | 229 | High | Work In Progress | Pending | 35268 | Al Kheesa | 70 | 57 | 57 | [6 empty] | 64 | 64 | [32 empty] | 7821 | 7821 | Completed | Pending | Pending | Pending | Pending | 29-P5 |  |  | 2026-08-18 | Pending | Completed
61 | 29-P6 | 245446 | 1195100 | 1A-1371/2021 | 2026-01-27 | 2026-01-26 | 816608/ 827265/ 836330 | Approved/ Printed | 2026-02-16 | 2026-11-16 | 2026-10-26 | 2026-09-12 | Backfilling | 30 | Scheme Normal | 229 | High | Work In Progress | Pending | 35268 | Al Kheesa | 70 | 138 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 19 | 19 | 16 | 16 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25974 | 25974 | Completed | Pending | Pending | Pending | Pending | 29-P6 |  |  | 2026-08-30 | Pending | Completed
62 | 30 | 246090 | 1199102 | 1A-624/2024 | 2026-02-09 | 2026-02-08 | Pending | Pending | Pending | Pending | 2026-08-08 | 2026-09-12 | Pending |  | Scheme Normal | 216 | High | Hold By KM | Pending | 13815 | Umm Slal / Al Kharatiyat | 71 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7495 | 0 | Pending | Pending | Pending | Work In Progress | Pending | 30 |  | 0 | PENDING | Pending | Hold By KM
63 | 31P-1 | 246091 | 1199104 | 1A-908/2025 | 2026-02-09 | 2026-02-08 | 817500 | Approved/ Printed | 2026-03-03 | 2026-08-20 | 2026-08-08 | 2026-04-30 | Backfilling | 30 | Scheme Normal | 70 | High | Invoiced | Not Required | 35409 | Al Wukair | 91 | 478.91 | 478.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26062.23 | 26062.23 | Invoiced | Closed | Invoiced | Received | INV-05 | 31 P-1 |  | 26062.23 | 2026-04-14 | Received | Invoiced
64 | 31P-2 | 246091 | 1199104 | 1A-908/2025 | 2026-02-09 | 2026-02-08 | 817500 | Approved/ Printed | 2026-03-03 | 2026-08-20 | 2026-08-08 | 2026-05-11 | Backfilling | 30 | Scheme Normal | 70 | High | Invoiced | Not Required | 35409 | Al Wukair | 91 | 566.65 | 566.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32157.45 | 32157.45 | Invoiced | Closed | Invoiced | Received | INV-05 | 31 P-2 |  | 32157.45 | 2026-05-07 | Received | Invoiced
65 | 31P-3 | 246091 | 1199104 | 1A-908/2025 | 2026-02-09 | 2026-02-08 | 817500 | Approved/ Printed | 2026-03-03 | 2026-08-20 | 2026-08-08 | 2026-06-01 | Backfilling | 30 | Scheme Normal | 70 | High | Invoiced | Not Required | 35409 | Al Wukair | 91 | 286.53 | 286.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17266.09 | 17266.09 | Invoiced | Closed | Invoiced | Received | INV-06 | 31 P-3 |  | 17266.09 | 2026-05-12 | Received | Invoiced
66 | 32-P1 | 246096 | 1199109 | 1A-877/2025 | 2026-02-09 | 2026-02-08 | 817501 | Approved/ Printed | 2026-03-08 | 2026-08-20 | 2026-08-08 | 2026-06-01 | Backfilling | 30 | Scheme Normal | 113 | High | Completed | Not Required | 21134 | Al Matar Al Qadeem | 45 | 448 | 448 | 0 | 0 | 0 | 0 | 110 | 110 | 0 | 0 | 520 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101029 | 101029 | Completed | Pending | Pending | Pending | Pending | 32-P1 |  | 0 | 2026-05-10 | Pending | Phase-2 Reinstatement Rectification Pending
67 | 32-P2 | 246096 | 1199109 | 1A-877/2025 | 2026-02-09 | 2026-02-08 | 817501 | Approved/ Printed | 2026-03-08 | 2026-08-20 | 2026-08-08 | 2026-07-01 | Backfilling | 30 | Scheme Normal | 143 | High | Completed | Not Required | 21134 | Al Matar Al Qadeem | 45 | 473.52 | 473.52 | 37.12 | 37.12 |  |  | 220 | 220 |  |  | 945 | 945 | [6 empty] | 2 | 2 | 2 | 2 | [20 empty] | 170584.8 | 170584.8 | Completed | Pending | Pending | Pending | Pending | 32-P2 |  | 0 | 2026-06-21 | Pending | Phase-2 Reinstatement Rectification Pending
68 | 32-P3 | 246096 | 1199109 | 1A-877/2025 | 2026-02-09 | 2026-02-08 | 817501 | Approved/ Printed | 2026-03-08 | 2026-08-20 | 2026-08-08 | 2026-07-07 | Backfilling | 30 | Scheme Normal | 149 | High | Completed | Not Required | 21134 | Al Matar Al Qadeem | 45 | 482 | 482 | 161.96 | 161.96 |  |  | 56 | 56 |  |  | 1695 | 1695 |  |  | 2 | 2 | 2 | 2 | 7 | 7 | 4 | 4 | 3 | 3 | [18 empty] | 286241.92 | 286241.92 | Completed | Pending | Pending | Pending | Pending | 32-P3 |  | 0 | 2026-06-28 | Pending | Phase-2 Reinstatement Rectification Pending
69 | 33-P1 | 246761 | 1203604 | 1A-870/2025 | 2026-02-22 | 2026-02-21 | 819033 | Approved/ Printed | 2026-03-11 | 2026-09-03 | 2026-08-22 | 2026-05-04 | Backfilling | 30 | Scheme Normal | 72 | High | Completed | Not Required | 5418 | Najma | 26 | 33.34 | 33.34 | 67.98 | 67.98 | 0 | 0 | 30 | 30 | 0 | 0 | 69 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23326.48 | 23326.48 | Invoiced | Closed | Invoiced | Received | INV-09 | 33 |  | 23326.48 | 2026-04-16 | Pending | Invoiced
70 | 34 | 246765 | 1203607 | 1A-575-2025 | 2026-02-22 | 2026-02-21 | 824062 | Approved/ Printed | 2026-05-12 | 2026-10-22 | 2027-02-22 | 2026-09-12 | Work In Progress |  | Scheme Normal | 203 | High | Work In Progress | Pending | 5834 | Al Wakra | 90 | 7286 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 250 | 0 | 1 | 0 | 4 | 0 | 4 | 0 | 48 | 0 | 48 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490988 | 0 | Work In Progress | Pending | Pending | Work In Progress | Pending | 34 |  | 0 | PENDING | Pending | Work In Progress
71 | 34-P1 | 246765 | 1203607 | 1A-575-2025 | 2026-02-22 | 2026-02-21 | 824062 | Approved/ Printed | 2026-05-12 | 2026-10-22 | 2027-02-22 | 2026-09-12 | Work In Progress |  | Scheme Normal | 203 | High | Work In Progress | Pending | 5834 | Al Wakra | 90 | 1178 | 1178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65494 | 65494 | Completed | Pending | Pending | Work In Progress | Pending | 34-P1 |  | 0 | 2026-07-19 | Pending | Reinstatement Pending
72 | 34-P2 | 246765 | 1203607 | 1A-575-2025 | 2026-02-22 | 2026-02-21 | 824062 | Approved/ Printed | 2026-05-12 | 2026-10-22 | 2027-02-22 | 2026-09-12 | Work In Progress |  | Scheme Normal | 203 | High | Work In Progress | Pending | 5834 | Al Wakra | 90 | 604 | 604 |  |  |  |  | 396 | 396 | [10 empty] | 2 | 2 | 0 | 0 | [20 empty] | 49212 | 49212 | Completed | Pending | Pending | Work In Progress | Pending | 34-P2 |  |  | 2026-08-12 | Pending | Reinstatement Pending
73 | 34-P3 | 246765 | 1203607 | 1A-575-2025 | 2026-02-22 | 2026-02-21 | 824062 | Approved/ Printed | 2026-05-12 | 2026-10-22 | 2027-02-22 | 2026-09-12 | Work In Progress |  | Scheme Normal | 203 | High | Work In Progress | Pending | 5834 | Al Wakra | 90 | 650 | 650 | 0 | 0 | 0 | 0 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35810 | 35810 | Completed | Pending | Pending | Work In Progress | Pending | 34-P3 |  |  | 2026-08-30 | Pending | Cable Laying Pending
74 | 34-P4 | 246765 | 1203607 | 1A-575-2025 | 2026-02-22 | 2026-02-21 | 824062 | Approved/ Printed | 2026-05-12 | 2026-10-22 | 2027-02-22 | 2026-09-12 | Work In Progress |  | Scheme Normal | 203 | High | Work In Progress | Pending | 5834 | Al Wakra | 90 | 444 | 444 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23532 | 23532 | Work In Progress | Pending | Pending | Work In Progress | Pending | 34-P4 |  |  | 2026-09-08 | Pending | Work In Progress
75 | 35 | 247038 | 1206425 | 1A-38/2020 | 2026-03-01 | 2026-03-02 | RO NA | Not Applied | N/A | N/A | 2026-09-01 | 2026-06-14 | Backfilling | 30 | Scheme Normal | 104 | High | Invoiced | Pending | P412 | Al Duhail | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464 | 464 | Invoiced | Closed | Invoiced | Received | INV-06 | 35 |  | 464 | 2026-06-12 | Received | Invoiced
76 | 36 | 247244 | 1207107 | 1A-1098/2025 | 2026-03-12 | 2026-03-11 | RO NA | Not Applied | N/A | N/A | 2026-07-12 | 2026-09-12 | Shut Down | 30 | Scheme Normal | 185 | High | Invoiced | Not Required |  | Umm Slal | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8100 | 8100 | Invoiced | Closed | Invoiced | Not Required | INV-02 | 36 |  | 8100 | 2026-03-26 | Received | Invoiced
77 | 37 | 247245 | 1207108 | 1A-19/2026 | 2026-03-12 | 2026-03-11 | RO NA | Not Applied | N/A | N/A | 2026-07-12 | 2026-09-12 | Shut Down | 30 | Scheme Normal | 185 | High | Invoiced | Not Required |  | Al Soudan South | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | Invoiced | Closed | Invoiced | Not Required | INV-02 | 37 |  | 9000 | 2026-03-26 | Received | Invoiced
78 | 38 | 247369 | 1207693 | 1A-882/2025 | 2026-03-24 | 2026-03-23 | 821173/ 821208 | Approved/ Printed | 2026-04-12 | 2026-10-08 | 2026-09-23 | 2026-09-12 | Work In Progress |  | Scheme Normal | 173 | High | Pending | Pending | 13115 | Madinat Khalifa-South | 34 | 775 | 0 | 0 | 0 | 0 | 0 | 147 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 8 | 0 | 2 | 0 | 0 | 0 | 650 | 0 | 900 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 |  | 61695 | 0 | Work In Progress | Pending | Pending | Work In Progress | Pending | 38 |  | 0 | PENDING | Pending | Work In Progress
79 | 38 P1 | 247369 | 1207693 | 1A-882/2025 | 2026-03-24 | 2026-03-23 | 821173/ 821208 | Approved/ Printed | 2026-04-12 | 2026-10-08 | 2026-09-23 | 2026-07-30 | Work In Progress |  | Scheme Normal | 129 | High | Pending | Pending | 13115 | Madinat Khalifa-South | 34 | 227 | 227 |  |  |  |  | 10 | 10 | [16 empty] | 250 | 250 | [16 empty] | 12931 | 12931 | Completed | Pending | Pending | Work In Progress | Pending | 38-P1 |  |  | 2026-07-28 | Pending | Completed
80 | 38 P2 | 247369 | 1207693 | 1A-882/2025 | 2026-03-24 | 2026-03-23 | 821173/ 821208 | Approved/ Printed | 2026-04-12 | 2026-10-08 | 2026-09-23 | 2026-08-29 | Work In Progress |  | Scheme Normal | 159 | High | Pending | Pending | 13115 | Madinat Khalifa-South | 34 | 232 | 232 | 36 | 36 |  |  | 118 | 118 |  |  | 45 | 45 | [6 empty] | 1 | 1 |  |  |  |  | 250 | 250 | [16 empty] | 27268 | 27268 | Completed | Pending | Pending | Work In Progress | Pending | 38-P2 |  |  | 2026-08-26 | Pending | Backfilling Pending
81 | 39 | 247372 | 1207697 | 1A-923/2025 | 2026-03-24 | 2026-03-23 | 821174 | Approved/ Printed | 2026-04-19 | 2026-10-08 | 2026-09-23 | 2026-09-12 | Returned | 0 | Scheme Normal | 173 | High | Pending | Pending | P273 | Dhukhan | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled | Cancelled | Cancelled | Not Required | Cancelled | 39 |  | 0 | PENDING | Not Required | Cancelled
82 | 40 | 247377 | 1207698 | 1A-661/2025 | 2026-03-24 | 2026-03-23 | 821314 | Approved/ Printed | 2026-05-06 | 2026-10-15 | 2026-09-23 | 2026-09-12 | Work In Progress |  | Scheme Normal | 173 | High | Pending | Pending | 10264 | Fareeq Al Amir/Murayakh/Al Soud | 54 | 9267 | 0 | 20 | 0 | 0 | 0 | 849 | 0 | 154 | 0 | 0 | 0 | 40 | 0 | 1 | 0 | 1 | 0 | 40 | 0 | 40 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 602231 | 0 | Work In Progress | Pending | Pending | Work In Progress | Pending | 40 |  | 0 | PENDING | Pending | Work In Progress
83 | 40-P1 | 247377 | 1207698 | 1A-661/2025 | 2026-03-24 | 2026-03-23 | 821314 | Approved/ Printed | 2026-05-06 | 2026-10-15 | 2026-09-23 | 2026-09-12 | Work In Progress |  | Scheme Normal | 173 | High | Pending | Pending | 10264 | Fareeq Al Amir/Murayakh/Al Soud | 54 | 233 | 233 | 40 | 40 |  |  | 51 | 51 | 46 | 46 | 45 | 45 | [30 empty] | 27219 | 27219 | Completed | Pending | Pending | Work In Progress | Pending | 40-P1 |  |  | 2026-08-24 | Pending | Backfilling Pending
84 | 41 | 248162 | 1213547 | 1A-128/2026 | 2026-04-06 | 2026-04-05 | 833649 | Approved/ Printed | 2026-08-06 | 2027-01-24 | 2026-10-06 | 2026-09-12 | Work Not Started |  | Scheme Normal | 160 | High | Pending | Pending | 23390 | Al Ghanim Al Qadeem-South | 16 | 550 | 0 | 10 | 0 | 0 | 0 | 100 | 0 | 200 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54225 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 41 |  | 0 | PENDING | Pending | Hold By KM
85 | 42 | 248323 | 1214391 | 1A-59/2026 | 2026-04-08 | 2026-04-07 | 824518 | Approved/ Printed | 2026-05-07 | 2026-10-29 | 2026-10-08 | 2026-09-12 | Work In Progress |  | Scheme Normal | 158 | High | Pending | Pending | 29510 | Mesaieed-Town | 92 | 60 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 19 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35235 | 0 | Work In Progress | Pending | Pending | Work In Progress | Pending | 42 |  | 0 | PENDING | Pending | Hold By KM
86 | 42-P1 | 248323 | 1214391 | 1A-59/2026 | 2026-04-08 | 2026-04-07 | 824518 | Approved/ Printed | 2026-05-07 | 2026-10-29 | 2026-10-08 | 2026-09-12 | Work In Progress |  | Scheme Normal | 158 | High | Pending | Pending | 29510 | Mesaieed-Town | 92 | 1160 | 1160 | 166.5 | 166.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77105.5 | 77105.5 | Completed | Pending | Pending | Work In Progress | Pending | 42-P1 |  |  | 2026-08-16 | Pending | Backfilling Pending
87 | 43 | 248346 | 1214450 | 1A-364/2024 | 2026-04-08 | 2026-04-07 | Pending | Not Applied | Pending | Pending | 2026-10-08 | 2026-09-12 | Work Not Started |  | Scheme Normal | 158 | High | Pending | Pending | 0341 | New Markets | 07 | 2800 | 0 | 30 | 0 | 0 | 0 | 1 | 0 | 2000 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 8 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313600 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 43 |  | 0 | PENDING | Pending | Hold By KM
88 | 44 | 248819 | 1217372 | 1A-958/2025 | 2026-04-15 | 2026-04-14 | ROW | RO Not Required | N/A | N/A | 2026-10-15 | 2026-09-12 | Work Not Started |  | Scheme Normal | 151 | High | Pending | Pending | P217 | Al Khor | 74 | 550 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31200 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 44 |  | 0 | PENDING | Pending | Hold By KM
89 | 45 | 249704 | 1224023 | 1A127/2026 | 2026-05-04 | 2026-05-03 | 827270 | Approved/ Printed | 2026-06-09 | 2026-11-16 | 2026-11-04 | 2026-09-12 | Work Not Started |  | Scheme Normal | 132 | High | Pending | Pending | 3353 | New District of Doha | 66 | 1600 | 0 | 1 | 0 | 0 | 0 | 500 | 0 | 500 | 0 | 1 | 0 | 90 | 0 | 2 | 0 | 2 | 0 | 10 | 0 | 10 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211352 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 45 |  | 0 | PENDING | Pending | Hold By KM
90 | 46 | 250227 | 1227987 | 1A-926-2025 | 2026-05-13 | 2026-05-14 | ROW | RO Not Required | N/A | N/A | 2026-11-14 | 2026-09-12 | Work Not Started |  | Scheme Normal | 121 | Medium | Pending | Pending | 8454 | Al Thakhira | 75 | 60 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4002 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 46 |  | 0 | PENDING | Pending | Hold By KM
91 | 47 | 250231 | 1228008 | 1A-42-2026 | 2026-05-13 | 2026-05-14 | 828215 | Approved/ Printed | 2026-06-21 | 2026-11-26 | 2026-11-14 | 2026-09-12 | Work In Progress |  | RI-Primary SS | 121 | High | Pending | Pending | P739 | Al Soudan South | 55 | 4000 | 0 | 20 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 285 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 15 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 414550 | 0 | Work In Progress | Pending | Pending | Work In Progress | Pending | 47 |  | 0 | PENDING | Pending | Work In Progress
92 | 48-P1 | 250631 | 1230807 | 1A-248-2026 | 2026-05-23 | 2026-05-24 | Pending | Approved/ Printed | 2026-06-07 | 2026-11-26 | 2026-11-24 | 2026-07-09 | Backfilling | 30 | RI-Load Flow | 46 | Very High | Completed | Required | 15196 | Legtaifiyah | 66 | 474 | 474 |  | 0 | 0 | 0 | 474 | 474 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44082 | 44082 | Completed | Pending | Pending | Pending | Pending | 48-P1 |  | 0 | 2026-06-21 | Pending | Completed
93 | 48-P2 | 250631 | 1230807 | 1A-248-2026 | 2026-05-23 | 2026-05-24 | Pending | Approved/ Printed | 2026-06-07 | 2026-11-26 | 2026-11-24 | 2026-07-09 | Backfilling | 30 | RI-Load Flow | 46 | Very High | Completed | Required | 15196 | Legtaifiyah | 66 | 500 | 500 |  | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48030 | 48030 | Completed | Pending | Pending | Pending | Pending | 48-P2 |  | 0 | 2026-07-05 | Pending | Completed
94 | 48-P3 | 250631 | 1230807 | 1A-248-2026 | 2026-05-23 | 2026-05-24 | Pending | Approved/ Printed | 2026-06-07 | 2026-11-26 | 2026-11-24 | 2026-07-09 | Backfilling |  | RI-Load Flow | 46 | Very High | Work In Progress | Required | 15196 | Legtaifiyah | 66 | 144 | 144 | 48 | 48 |  |  | 140 | 140 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27623 | 27623 | Completed | Pending | Pending | Work In Progress | Pending | 48-P3 |  | 0 | 2026-07-15 | Pending | Completed
95 | 48-P4 | 250631 | 1230807 | 1A-248-2026 | 2026-05-23 | 2026-05-24 | Pending | Approved/ Printed | 2026-06-07 | 2026-11-26 | 2026-11-24 | 2026-07-09 | Backfilling | 30 | RI-Load Flow | 46 | Very High | Work In Progress | Required | 15196 | Legtaifiyah | 66 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 5 | 5 | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7535 | 7535 | Completed | Pending | Pending | Work In Progress | Pending | 48-P4 |  |  | 2026-08-02 | Pending | Completed
96 | 49 | 250810 | 1232563 | 1A-202-2026 | 2026-05-31 | 2026-05-31 | NA | RO Not Required | N/A | N/A | 31/11/2026 | 2026-09-12 | Work Not Started |  | RI-Load Flow | 104 | Low | Pending | Pending | P728 | Old Airport | 48 | 200 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 16 | 0 | 8 |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27880 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 49 |  | 0 | PENDING | Pending | Hold By KM
97 | 50 | 251033 | 1234577 | 1A-265-2026 | 2026-06-07 | 2026-06-07 | 830900 | Approved/ Printed | 2026-06-22 | 2026-12-15 | 2026-12-06 | 2026-09-12 | Work In Progress |  | RI-Load Flow | 97 | Low | Pending | Pending |  | Al Wakra | 90 | 30 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16645 | 0 | Work In Progress | Pending | Pending | Work In Progress | Pending | 50 |  | 0 | PENDING | Pending | Work In Progress
98 | 50-P1 | 251033 | 1234577 | 1A-265-2026 | 2026-06-07 | 2026-06-07 | 830900 | Approved/ Printed | 2026-06-22 | 2026-12-15 | 2026-12-06 | 2026-09-12 | Work In Progress |  | RI-Load Flow | 97 | Low | Pending | Pending |  | Al Wakra | 90 | 590 | 590 | 102 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53064 | 53064 | Completed | Pending | Pending | Work In Progress | Pending | 50-P1 |  |  | 2026-08-30 | Pending | Cable Laying Pending
99 | 51 | 252396 | 1243518 | 1A-47-2013 | 2026-07-05 | 2026-07-05 | 838288 | Approved/ Printed | 2026-08-16 | 2027-02-11 | 2027-01-05 | 2026-09-12 | Work Not Started |  | RI-Load Flow | 69 | Low | Pending | Pending | 12361 | Umm Slal | 71 | 582 | 0 | 1 | 0 | 0 | 0 | 100 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6 | 0 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42383 | 0 | Not Started | Pending | Pending | Work In Progress | Pending | 51 |  | 0 | PENDING | Pending | Hold By KM
100 | 52 | 253333 | 1251556 | 1A-214-2026 | 2026-07-31 | 2026-08-01 | Pending | RO Not Required | N/A | N/A | 2027-02-01 | 2026-09-12 | Work Not Started |  | RI-Load Flow | 42 | Low | Pending | Pending | 38811 | Abu Nakhla/Mukainess | 81 | 600 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46872 |  | Not Started | Pending | Pending | Pending | Pending | 52 |  |  | PENDING | Pending | Hold By KM
101 | 53 | 254901 | 1261932 | 1A-269/2026 | 2026-09-03 | 2026-09-03 | Pending | Not Applied | Pending | Pending | 2027-03-03 | 2026-09-12 | Work Not Started |  | RI-Load Flow | 9 | Low | Pending | Pending | 9938 | Al Rayyan Al Jadeed/Muaither N | 81 | 640 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  | 1 |  | 0 | 0 | 2 |  | 2 |  | 8 |  | 6 |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44860 |  | Not Started | Pending | Pending | Pending | Pending | 53 |  |  | PENDING | Pending | Hold By KM
0
[23 empty] | 62432.91 | 25350.91 | 3243.1 | 2029.1 | 5 | 0 | 12252 | 7725 | 5488 | 960 | 7392 | 6884 | 2161 | 1683 | 38 | 16 | 130 | 114 | 554 | 239 | 449 | 173 | 225 | 72 | 6002 | 5152 | 6980 | 80 | 1 | 0 | 6 | 0 | 8 | 2 | 1 | 0 | 0 | 0 | 3 | 2 | 8 | 2 | 7550386.93 | 4215447.93 | [7 empty] | 1851418.71
0
0
0
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: MOC-40 DAYS, BP/OFF LOAD-90DAYS
Note on BP2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: to be planned/Planned/Finished
Note on BR2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending/Invoiced
Note on BS2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending/Invoiced/Work in progress/Hold
Note on BW2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: manul type -invoiced vale
Note on BY2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending/Done
Note on BZ2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending/Invoiced/Work in progress/Hold

## Project Summary
PROJECT SUMMARY REPORT |  | Updated up to 12-09-26
PROJECT : | GTC-1236/24
Project Start Date | 2025-09-11
Project End Date | 2028-09-11
DETAILS | AMOUNT | % | Remarks
TOTAL CONTRACT VALUE (Original) | 20303300
TOTAL ISSUED VALUE | 7550386.93 | 37.19%
TOTAL COMPLETED VALUE | 4215447.93 | 20.76%
BALANCE TO BE ISSUED | 12752913.07 | 62.81%
Work to be Executed | 3334939 | 16.43%
Work in Progress | 1804981 | 8.89%
TOTAL INVOICED VALUE AS OF (01-10-23) | 1851418.71 | 43.92%
TOTAL INVOICED VALUE FROM CONTRACT | 1851418.71 | 9.119%
BALANCE VALUE AS OF CONTRACT | 18451881.29 | 90.88%
READY FOR INVOICE | 2364029.22 | 31.31%
BALANCE TO BE INVOICED | 16087852.07 | 79.24%
CWR Wise Details
Details | No of CWR | Issued Value | Completed Value | Issued Length | Completed Length | Remarks
Total CWR Issued By KM (Nos) | 53 | 7550386.93 | 4215447.93 | 62432.91
Cancelled/Return/Not issued (Nos) | 4 |  | - | 0
Invoiced (Nos) | 0 | 1851418.71 | 1851418.71 | 13575.39
Ready For Invoice (Nos) | 0 | 2364029.22 | 2364029.22 | 0
Work Completed (Nos) | 0 | 2326547.22 | 2326547.22 | 11181.52
Not Started CWR (Nos) | 0 | 1559945 | 0 | 14799
Work In Progress (Nos) | 0 | 1804981 | 37482 | 22862
| 0 | 9906921.15 | 6579477.15 | 62417.91 | 0

## lists
RO STATUS | Date Type | Type of job | Priority | SITE STATUS | Baladiya Permit | location | Zone | Final Status | Scheme Closure Form | 'Invoice Status | 'WCC Status | 'Final Inspection Status | 'Final Site Status
RO Not Required | Backfilling | Reinforcement Normal | Low | Cancelled | Required | Umm Slal | 71 | Cancelled | Cancelled | Pending | Pending | Pending | Work Not Started
Not Applied | Reinstatement | RI-Primary SS | Medium | Work In Progress | Not Required | Al Khulaifat | 56 | Work In Progress | Not Required | Invoiced | Received | Work In Progress | Work In Progress
Shared RO | Shut Down | Scheme Normal | High | Completed | Pending | Mesaieed -Town | 92 | Completed | Closed | Cancelled | Work In Progress | Received | Cable Laying Pending
In Review | Returned | RI-QE-Mesaieed | Very High | Pending | Cancelled | Mesaieed-Industrial Area | 93 | Pending | Pending | Work In Progress | Not Required | Not Required | Backfilling Pending
Waiting For TDP Drawing | Cancelled | RI-QE-Dukhan |  | Invoiced |  | New District of Doha | 66 | Invoiced | Work In Progress | Not Started |  |  | Reinstatement Pending
Technical Verification | Work In Progress | Scheme-QE-Mesaieed |  | Hold By KM |  | Raudat Rashid | 82 | Not Started |  | Started |  |  | Phase-2 Reinstatement Rectification Pending
Pending Fees | Pending | Scheme-QE-Dukhan |  | Ready To Start |  | Al Shahhniya | 80 | [5 empty] | Final R/I Rectification Pending
Approved/ Printed | Work Not Started | RI-Load Flow |  | Site Obstruction |  | Umm Bab | 84 | [5 empty] | Phase-2 Reinstatement Pending
[6 empty] | Al Kheesa | 70 | [5 empty] | Hold By KM
[6 empty] | Al Kharara | 95 | [5 empty] | Completed
[6 empty] | Al Wukair | 91 | [5 empty] | Invoiced
[6 empty] | Murrah / Al Aziziya | 55 | [5 empty] | Cancelled
[6 empty] | Al Aziziya | 55
[6 empty] | Al Khulaifat Al Jadeeda | 56
[6 empty] | Bin Omran | 37
[6 empty] | Al Madar Al Qadeem | 45
[6 empty] | Al Mansoura / Bin Dirham | 25
[6 empty] | Al Nasraniya | 85
[6 empty] | Umm Slal / Al Kharatiyat | 71
[6 empty] | Al Matar Al Qadeem | 45
[6 empty] | Najma | 26
[6 empty] | Al Wakra | 90
[6 empty] | Al Duhail | 30
[6 empty] | Al Soudan South | 55
[6 empty] | Madinat Khalifa-South | 34
[6 empty] | Dhukhan | 86
[6 empty] | Fareeq Al Amir / Murayakh / Al Soud | 54
[6 empty] | Al Ghanim Al Qadeem (South) | 16
[6 empty] | New Markets | 7
[6 empty] | Al Khor | 74